## Sheet1
Milestone | Main Task | Subtasks | Assigned To | Progress (%)
4.5 - Backend Infrastructure & Core Functionality | Hosting Setup | Choose hosting provider; Configure PHP/database; Upload files to host; Verify file structure | Ben & Damon | 0
4.5 - Backend Infrastructure & Core Functionality | Database Creation | Design schema; Define relationships; Create test data; Document database structure | Cullen & Doryan | 0
4.5 - Backend Infrastructure & Core Functionality | PHP Backend Setup | Establish routing system; Connect PHP to DB; Create config file; Test data retrieval | Ben & Cullen | 0
4.5 - Backend Infrastructure & Core Functionality | Admin Authentication | Create login form; Implement password hashing; Session handling; Logout function | Damon | 0
4.5 - Backend Infrastructure & Core Functionality | Admin Dashboard | Design dashboard layout; Display stats; Add navigation; Restrict access | Ben & Damon | 0
4.5 - Backend Infrastructure & Core Functionality | Image Upload System | Create upload form; Validate image; Store path in DB; Display images dynamically | Cullen | 0
4.5 - Backend Infrastructure & Core Functionality | Testing & Documentation | Write test cases; Verify CRUD; Record bugs; Update documentation | All members | 0
4.5 - Backend Infrastructure & Core Functionality | Planning Document | Record backend progress; Add diagrams; Update timeline and tasks | Ben | 0
4.75 - Public-Facing Features & Forms | Dynamic Gallery Display | Fetch gallery data; Render images dynamically; Add lightbox; Test multiple items | Doryan | 0
4.75 - Public-Facing Features & Forms | Gallery Enhancements | Add sorting/filtering; Style responsive grid; Optimize loading | Damon | 0
4.75 - Public-Facing Features & Forms | Contact Form Integration | Create contact form; Validate input; Store in DB | Cullen | 0
4.75 - Public-Facing Features & Forms | Contact Form Admin View | Display messages in admin; Add delete/view; Implement pagination/search | Ben & Cullen | 0
4.75 - Public-Facing Features & Forms | Booking System (User Side) | Create booking form; Store bookings; Generate confirmation | Doryan | 0
4.75 - Public-Facing Features & Forms | Booking Backend Process | Create DB table; Develop CRUD functions; Validate overlaps | Damon | 0
4.75 - Public-Facing Features & Forms | Booking Admin Management | Display bookings in dashboard; Update status; Add filter options | Ben & Damon | 0
4.75 - Public-Facing Features & Forms | Cross-Browser Testing | Test in major browsers; Check responsiveness; Log issues | All members | 0
4.75 - Public-Facing Features & Forms | Planning Document | Update milestone report; Add screenshots; Document new PHP functions | Ben | 0